## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Renuka Selvi K | 2026-02-10 | Unused imports were not being detected correctly for certain python files | Sprint 1 | Self | Logical | Improved AST traversal logic to correctly identify unused imports | 2026-02-11 | Closed | Issue resolved and validated with sample programs
2 | Renuka Selvi K | 2026-02-14 | PEP8 style violations were not highlighted consistently in the output | Sprint 1 | Self | Standards | Integrated stricter PEP8 checks and improved formatting rules | 2026-02-15 | Closed | Style detection accuracy improved
3 | Renuka Selvi K | 2026-02-20 | Syntax errors were not detected for multi-line statements | Sprint 2 | self |  | Improved parser to handle multi-line syntax cases | 2026-02-21 | Closed | Fixed and validated with multiple multi line test cases
4 | Renuka Selvi K | 2026-02-25 | Logical errors were not identified in nested conditions | Sprint 2 | self | Logical | Enhanced rule-based logic detection for nested structures | 2026-02-26 | closed | Issue resolved ; detection accuracy improved
5 | Renuka Selvi K | 2026-02-28 | Error explanations were too vague for beginners | Sprint 2 | Self | Standards | Improved Explanation clarity with detailed messages | 2026-03-01 | closed | Enhanced explanations; user feedback improved
6 | Renuka Selvi K | 2026-02-08 | AST parsing failed for large Python files | Sprint 1 | Self |  | Optimized parsing logic and memory handling | 2026-02-10 | closed | Performance optimized; tested with large inputs
7 | Renuka Selvi K | 2026-03-05 | Optimization suggestions were not generated for some loops | Sprint 3 | Self | Logical | Improved pattern detection for loop optimization | 2026-03-07 | closed | Optimization logic updated and verified
8 | Renuka Selvi K | 2026-03-17 | UI did not display categorized feedback properly | Sprint 4 | Self |  | Fixed frontend rendering logic for categorized results | 2026-03-20 | closed | UI rendering fixed and tested successfully
9 | Renuka Selvi K | 2026-03-26 | API response delay caused slow analysis results | Sprint 4 | Self |  | Optimized backend API calls and reduced latency | 2026-03-27 | closed | Response time reduced; system performance improved
10 | Renuka Selvi K | 2026-03-28 | System crashed when empty input was submitted | Sprint 1 | Self | Standards | Added input validation to handle empty submissions | 2026-03-30 | closed | Edge case handled; input validation added

## Sheet2
Logical
User Interface
Maintainability
Standards
Others